## Estimations
Sr. No | Page/Exercise | Activity | Time (Man hours) | Total hrs
1 | Root Template
|  | Feasibility Analysis | 8
|  | Setup and environment | 8
|  | Typography / Style guide Integration |  |  | Add-On - Priyanka
|  | Header | 4
|  | Footer | 4
|  | Quantity Stepper | 16
|  | Breadcrumb | 4
44
2 | PLP
|  | Sub Category Text | 4
|  | Filter Products Dropdown / side panel | 16
|  | Filter by Brands / Categories / Department / Price / Ratings |  |  | Add-On - Priyanka
|  | Total Items | 4
|  | Recommended Filter | 4
|  | Product Listing 24 Items | 2
|  | Ratings Section | 4
34
3 | PDP
|  | Product Image | 4
|  | On click of image, update main product image. |  |  | Add-on - Priyanka
|  | Product Details | 4
|  | Size | 16
|  | Scrollable Color Bar | 16
|  | Add to Cart | 16
|  | Three Accordions | 16
72
4 | Order Details Page
|  | Order Details | 4
|  | Product Details | 4
|  | Buy Button | 1
|  | Price Information | 1
|  | Rewards Points / Animation | 4
Payment Method
Payment Details
14
| Total of Above Pages |  |  | 164
5 | Responsive |  |  | 8
6 | Accessibility |  |  | 8
7 | Testing |  |  | 8
8 | Buffer |  |  | 16
| GROSS TOTAL EFFORTS (Man Hours) |  |  | 204
| GROSS TOTAL EFFORTS (Man Days) |  |  | 25

## Assumptions
Assumptions
1. Browser Support Required: Windows: IE 11 and Edge, Chrome, Firefox, Mac: Safari, Chrome, Firefox Android: Chrome iOS: Safari
2. Initial setup includes times for finalizing approach
3. Change in requirements will vary the timelines
4. Only VD`s will be used as design reference.
Assumptions
. Initial Setup will include for feasibility test for browsers